## Slide 1
INDUSTRIAL APPLICATIONS
University of Pisa
MoodPilot
PROJECT DISCUSSION
PIERFRANCESCO FOGLIA
ANTONIO COSIMO PRETE
PROFESSORS
MASTER’S DEGREE IN COMPUTER ENGINEERING
GIOVANNI LIGATO GIUSEPPE SORIANO
STUDENTS
(

## Slide 2
CURRENT CHALLENGES IN RIDE-SHARING SERVICES
Existing two-way rating systems are limited in providing a comprehensive view of the actual driving quality.
Difficulty in obtaining real-time feedback about the passenger’s experience during the ride.
Subjective passenger ratings can be inconsistent or influenced by temporary emotions.
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 3
DRIVERS
Risk of unfair ratings affecting opportunities, lack of actionable feedback.
COMPANIES
Difficulty in ensuring consistent quality and reliability across drivers, reliance on subjective feedback.
PASSENGERS
Limited tools to express real-time concerns. Potential safety and comfort issues not fully addressed.
IMPACT ON STAKEHOLDERS
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 4
SO, WHAT’S THE PROBLEM
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 5
How can we achieve a more objective, real-time assessment of driver performance that reflects both safety and passenger comfort ?
How can ride-sharing platforms move beyond basic ratings to gain insights that improve service quality ?
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 6
GOAL OF THE RESEARCH
Integrate new technologies like Facial Expression Recognition and telemetry for a data-driven, unbiased evaluation system.
1
Provide a holistic view of driver performance that includes passenger comfort and safety metrics.
2
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 7
STATE OF THE ART
FACIAL EXPRESSION RECOGNITION IN AUTOMOTIVE CONTEXTS
ENHANCEMENT OF PASSENGER SAFETY AND EXPERIENCE
Provides a comprehensive literature survey of work addressing the problem of human emotion recognition in an automotive context.
DRIVER EMOTION RECOGNITION FOR INTELLIGENT VEHICLES: A SURVEY (2020)
[1]
AUDIOVISUAL AFFECT RECOGNITION FOR AUTONOMOUS VEHICLES: APPLICATIONS, CHALLENGES, AND OPPORTUNITIES (2023)
[2]
Examines the use of audiovisual emotion recognition in autonomous vehicles, highlighting technical challenges and opportunities for improving human-machine interaction.
REVIEW AND PERSPECTIVES ON HUMAN EMOTION FOR CONNECTED AUTOMATED VEHICLES (2023)
[3]
Discusses the importance of recognizing human emotions in connected automated vehicles, focusing on implications for passenger safety and experience.
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 8
STATE OF THE ART
Analyzes how platform-driven reputation systems impact service quality in ride-sharing, highlighting benefits and limitations in maintaining consistent quality.
PLATFORM-MEDIATED REPUTATION SYSTEMS IN THE SHARING ECONOMY (2020)
[4]
A SYSTEMATIC LITERATURE REVIEW OF RIDE-SHARING PLATFORMS, USER FACTORS, AND BARRIERS (2021)
[5]
Provides a systematic review of ride-sharing platforms, focusing on user adoption factors and barriers, including the effectiveness of rating systems.
UNDERSTANDING RIDE-SHARING SYSTEMS IN URBAN AREAS: LOCATION, USERS, AND BARRIERS (2020)
[6]
Explores ride-sharing in urban areas, examining the role of location, user types, and system barriers with specific reference to two-way rating mechanisms.
TWO-WAY RATING SYSTEMS FOR DRIVER EVALUATION
EFFECTIVENESS IN ASSESSING DRIVER PERFORMANCE
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 9
GLOBAL MARKET ANALYSIS
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 10
UBER
DRIVER’S AVERAGE RATING
POST-TRIP
EVALUATION
PASSENGER’S AVERAGE RATING
Ratings are anonymous to ensure honest feedback.
At the end of each ride, passengers rate drivers and vice versa.
Calculated based on the last 500 ratings received. A high rating improves visibility for future trip requests, while a consistently low rating may lead to account deactivation.
Calculated using all the trips taken. Passengers with lower ratings may experience difficulty finding drivers.
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 11
DIDI CHUXING
AI-DRIVEN SAFETY ALERTS
Machine Learning algorithms analyze telemetric data and provide real-time safety alerts to drivers, reducing risky behaviors and ensuring safer rides.
TELEMETRIC MONITORING
Uses vehicle sensors to track driving behaviors, such as: sudden braking, sharp turns, accelerations. These metrics are analyzed alongside passenger ratings to provide a more objective evaluation of driver performance.
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 12
THE IDEA
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 13
PASSENGER
DRIVER
FACIAL
EXPRESSION
RECOGNITION
RATING
MoodPilot
(
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 14
FACIAL EXPRESSION RECOGNITION
INTEGRATION
FER algorithms analyze emotional states, such as:
During the ride, a camera monitors the passenger’s facial expressions in real time.
COMFORT: Smiles, neutral expressions.
DISCOMFORT: Frowns, signs of stress or frustration.
AUTO-FILLED FEEDBACK FORMS
EMOTION-BASED
Based on detected emotions, the system auto-fills a feedback form. Captures key metrics such as comfort level, perceived safety, and overall satisfaction. Generates a final passenger rating by summarizing the feedback from the analyzed expressions.
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 15
THE AUTO-FILLED FEEDBACK FORM
COMFORT DURING THE RIDE
1
HOW WOULD YOU RATE YOUR LEVEL OF COMFORT THROUGHOUT THE RIDE?
1: VERY UNCOMFORTABLE - 5: VERY COMFORTABLE
PERCEIVED SAFETY
2
HOW SAFE DID YOU FEEL DURING THE TRIP?
1: VERY UNSAFE - 5: VERY SAFE
OVERALL EXPERIENCE
3
HOW WOULD YOU RATE YOUR OVERALL EXPERIENCE?
1: VERY POOR - 5: EXCELLENT
SPECIFIC MOMENTS
4
WERE THERE ANY SPECIFIC MOMENTS DURING THE RIDE THAT CAUSED DISCOMFORT OR CONCERN?
NONE
A FEW MOMENTS (E.G., SUDDEN BRAKING OR HARSH TURNS)
FREQUENT MOMENTS (PERSISTENT DISCOMFORT THROUGHOUT THE RIDE)
RATING
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 16
SOLUTIONS COMPARISON
MoodPilot
7. PRIVACY AND CONSENT
1. PASSENGER COMFORT ASSESSMENT
5. PASSENGER STRESS DETECTION
3. CONTINUOUS DRIVER MONITORING
2. AUTOMATIC EVALUATION
6. TWO-WAY RATING SYSTEM
4. OBJECTIVE FEEDBACK
(
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 17
POSSIBLE RISKS
WILL PASSENGERS FEEL AT EASE KNOWING THEIR EMOTIONS ARE RECORDED AND USED FOR EVALUATION?
IS THE MARKET READY TO INTRODUCE SUCH AN INNOVATION?
1.
2.
I RISCHI NON SONO SU QUESTE COSE; MA DAL PUNTO DI VISTA PROGETTUALE (COME SE AZIENDA CHE CI FORNISCE COMPONENTE FALLISCE)
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 18
F1.
Facial Expression Recognition
The system must detect and analyze passengers' facial expressions in real-time using cameras integrated into the vehicle.
F2.
Feedback Evaluation via Form
The FER system must automatically complete a form based on the emotions detected during the trip.
The results of this form must then be processed to generate an overall numerical score that reflects the passenger's rating of the driver.
F3.
Collection, Processing, and Management of Evaluations
The system must record data collected during each trip, including the overall numerical score derived from the questionnaire.
The driver's overall rating must be calculated as a weighted average of the last 500 ratings received.
Collected data must be securely stored for subsequent analysis and to ensure the traceability of evaluations
FUNCTIONAL REQUIREMENTS
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 19
FUNCTIONAL REQUIREMENTS
F4.
User Interface
For Passengers: The interface must allow passengers to review and manually edit responses to the automatically generated questionnaire.
For Drivers: The interface must include a feature for drivers to rate passenger behavior at the end of each trip.
F5.
Data Privacy and Security
All collected data, including video footage, questionnaire responses, and evaluations, must be handled in compliance with privacy regulations.
Data encryption must be implemented both at rest and in transit.
Passengers and drivers must be informed and explicitly consent to the collection and processing of personal data.
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 20
NON-FUNCTIONAL REQUIREMENTS and CONSTRAINTS
NF1.
Processing Speed
The system must complete facial expression detection within a maximum of 1 second per processed frame.
NF2.
Accuracy and Consistency
FER models must achieve a minimum accuracy of 80% in emotion recognition on a diverse and balanced dataset.
NF3.
System Usability
The user interface for passengers and drivers should require no more than 3 steps to complete evaluations or provide feedback.
The system setup for new users or vehicles must be completed within 10 minutes.
NF4.
Scalability and Extensibility
The architecture must support the addition of new FER models or customized questionnaires without more than 1 hour of downtime during updates.
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 21
NON-FUNCTIONAL REQUIREMENTS and CONSTRAINTS
NF5.
Privacy Protection
Sensitive data must not be stored for more than 30 days, unless explicitly authorized by users for specific purposes.
NF6.
Resilience and Security
The system must ensure 99.9% uptime on a monthly basis, with scheduled downtime limited to a maximum of 4 hours per month.
All communications between the frontend and backend must be encrypted using TLS 1.3 standards.
NF7.
Resource Efficiency
The system must be optimized for a maximum power consumption of 5W on onboard devices, ensuring minimal impact on electric vehicle batteries.
The FER model must operate within 2 GB of RAM on embedded vehicle systems.
NF8.
Backend Technology
The backend must be implemented in Python to ensure compatibility with the pre-developed FER models.
It should be compatible with Python frameworks like Flask for high performance and easy extensibility.
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 22
NON-FUNCTIONAL REQUIREMENTS and CONSTRAINTS
NF1.
Processing Speed
The system must complete facial expression detection within a maximum of 1 second per processed frame.
NF2.
Accuracy and Consistency
FER models must achieve a minimum accuracy of 80% in emotion recognition on a diverse and balanced dataset.
NF3.
System Usability
The user interface for passengers and drivers should require no more than 3 steps to complete evaluations or provide feedback.
The system setup for new users or vehicles must be completed within 10 minutes.
NF4.
Scalability and Extensibility
The architecture must support the addition of new FER models or customized questionnaires without more than 1 hour of downtime during updates.
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 23
SYSTEM
ARCHITECTURE
FRONT-END
MOBILE APP
CAR CONTROLLER
FACIAL
EXPRESSION
RECOGNITION
MODEL
BACK-END
DATABASE
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 24
SYSTEM
ARCHITECTURE
FRONT-END
MOBILE APP
CAR CONTROLLER
BACK-END
DATABASE
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 25
WORK PACKAGES
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 26
1
WP
MOTIVATION
Un database ben progettato è fondamentale per archiviare e gestire in modo efficiente i dati raccolti dal sistema, tra cui valutazioni FER, feedback manuali e dati sensoriali provenienti dai veicoli. La struttura deve garantire velocità nelle query, integrità dei dati e scalabilità per gestire un numero crescente di veicoli e utenti.
MONTH/MAN
1 sviluppatore senior (backend/db) per 2 mesi (2 mesi/uomo).
GOALS
1. Progettare uno schema di database robusto, normalizzato e ottimizzato per le query principali.
2. Implementare il database su un server locale o cloud.
3. Garantire la scalabilità e l’integrità dei dati.
4. Ottimizzare le query per il backend e il sistema di reportistica.
MONTH 1
START
MONTH 2
END
TITLE
CONFIGURAZIONE E PROGETTAZIONE DEL DATABASE (DB)
CLASSIFICATION
RI (RESEARCH AND INNOVATION)
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 27
1
WP
MOTIVATION
A well-designed database is essential for efficiently storing and managing data collected by the system, such as FER evaluations, manual feedback, and sensor data from vehicles. Its structure must ensure query speed, data integrity, and scalability to handle an increasing number of vehicles and users.
1 project manager for 2 months (2 person-months).
GOALS
1. Design a robust, normalized database schema optimized for primary queries.
2. Deploy the database on a local or cloud server.
3. Ensure data scalability and integrity.
4. Optimize queries for the backend and reporting system.
MONTH 1
START
MONTH 2
END
TITLE
DATABASE CONFIGURATION AND DESIGN (DB)
CLASSIFICATION
RESEARCH and
INNOVATION
PERSON-MONTHS
1 senior developer (DB) for 2 months (2 person-months).
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 28
1
WP
TASKS
1. Requirements Analysis:
- Collect system-required data (FER, evaluations, feedback, sensor data).
- Identify relationships between main entities.
2. Schema Design:
- Define main tables (e.g., `Passengers`, `Drivers`, `Trips`, `FER_Data`, `Evaluations`).
- Normalize the schema to eliminate redundancies and ensure consistency.
3. Database Implementation:
- Create tables and define relationships (e.g., 1:N, N:N).
- Configure indexes to optimize primary queries.
4. Query Optimization:
- Develop queries for common operations (e.g., insert evaluations, calculate the average of the last 500 evaluations).
- Optimize performance on simulated datasets.
5. Testing and Validation:
- Verify referential integrity and query functionality.
- Simulate increasing loads to assess scalability.
MONTH 1
START
MONTH 2
END
CLASSIFICATION
RESEARCH and
INNOVATION
1 project manager for 2 months (2 person-months).
PERSON-MONTHS
1 senior developer (DB) for 2 months (2 person-months).
TITLE
DATABASE CONFIGURATION AND DESIGN (DB)
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 29
1
WP
DELIVERABLES
1. Database Schema: Documented ER diagram model.
2. Implemented Database: Fully operational database with all tables and defined relationships.
3. SQL Scripts: Scripts for table creation, constraints, and indexes.
4. Report: Documentation of primary queries and applied optimizations.
MONTH 1
START
MONTH 2
END
CLASSIFICATION
RESEARCH and
INNOVATION
MILESTONES
1. ER diagram delivery (end of Month 1).
2. Database implementation and working SQL scripts (mid-Month 2).
3. Query validation and final report (end of Month 2).
DEPENDENCIES AMONG WPS
- WP2 (Backend): Required to test communication between the database and API endpoints. Database design must be completed before proceeding with the backend.
- WP5 (Integration): Database must be complete and functional before system integration.
1 project manager for 2 months (2 person-months).
PERSON-MONTHS
1 senior developer (DB) for 2 months (2 person-months).
TITLE
DATABASE CONFIGURATION AND DESIGN (DB)
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 30
1
WP
MONTH 1
START
MONTH 2
END
CLASSIFICATION
RESEARCH and
INNOVATION
REQUIRED TOOLS OR SOFTWARE
- Relational Database: MySQL or PostgreSQL (already available).
- Modeling Tools: DbSchema or MySQL Workbench (already available).
- SQL Language: For database implementation and optimization (no additional cost).
- Profiling Tools: EXPLAIN for query analysis (available in chosen DBMS).
REQUIRED ROLES
- Database Developer: Expert in relational database design and optimization (MySQL or PostgreSQL).
COST PER ROLE (BASED ON PERSON-MONTHS)
- Database Developer: €5,000/month
- Project Manager: €6,000/month
TOTAL COST OF WP1
€22.000
1 project manager for 2 months (2 person-months).
PERSON-MONTHS
1 senior developer (DB) for 2 months (2 person-months).
TITLE
DATABASE CONFIGURATION AND DESIGN (DB)
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 31
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 32
2
WP
MOTIVATION
The backend is the core of the system, managing data flow between various components: database, car controller, and frontend. It must integrate the FER model, expose RESTful API endpoints, and ensure efficient management of evaluations and collected data, with a strong focus on security and scalability.
GOALS
1. Implement a robust and scalable backend in Python to manage data flow.
2. Integrate the FER model for automatic evaluations.
3. Expose RESTful API endpoints to communicate with the frontend and car controller.
MONTH 2
START
MONTH 4
END
TITLE
BACKEND DEVELOPMENT
CLASSIFICATION
RESEARCH and
INNOVATION
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 backend developers for 3 months (6 person-months).
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 33
2
WP
TASKS
1. Development Environment Setup:
- Configure the backend framework (e.g., Flask or FastAPI).
- Structure the project.
2. RESTful API Implementation:
- Create endpoints for communication with the car controller, frontend, and database (e.g., `/sendEvaluation`, `/getUserData`).
- Validate and authenticate API requests.
3. Database Integration:
- Connect to the database using an ORM (e.g., SQLAlchemy).
- Develop backend queries to handle complex data operations (e.g., calculate the average of the last 500 evaluations).
4. FER Model Integration:
- Implement functions to receive input from the car controller.
- Process and store FER data in the database.
5. Security and Privacy:
- Implement security protocols (e.g., TLS 1.3 for communications).
- Encrypt sensitive data.
- Create data management policies compliant with GDPR.
6. Testing and Validation:
- Test APIs (unit tests and integration tests).
- Simulate workloads to ensure scalability.
CLASSIFICATION
RESEARCH and
INNOVATION
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 backend developers for 3 months (6 person-months).
MONTH 2
START
MONTH 4
END
TITLE
BACKEND DEVELOPMENT
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 34
2
WP
DELIVERABLES
1. Operational Backend: Complete source code with API and FER model integration.
2. Technical Documentation: Details on implementation, API endpoints, and usage instructions.
3. Data Management Logic: Functions implemented to interact with the database and car controller.
4. Test Report: Results of integration tests and load simulations.
CLASSIFICATION
RESEARCH and
INNOVATION
MILESTONES
1. Delivery of basic working APIs (end of Month 2).
2. Completed database integration (end of Month 3).
3. Backend validation in a simulated environment (end of Month 4).
DEPENDENCIES AMONG WPS
- WP1 (Database): Database design must be completed to develop the backend.
- WP5 (Integration): The backend must be completed to integrate components.
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 backend developers for 3 months (6 person-months).
MONTH 2
START
MONTH 4
END
TITLE
BACKEND DEVELOPMENT
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 35
2
WP
CLASSIFICATION
RESEARCH and
INNOVATION
REQUIRED TOOLS OR SOFTWARE
- Backend Framework: Flask or FastAPI (available).
- Security Libraries: PyJWT for authentication, OpenSSL for encryption.
- ORM: SQLAlchemy or equivalent for database interaction.
- Testing Tools: Postman for API testing, pytest for automated tests.
REQUIRED ROLES
- Backend Developer: Specialist in Python, experienced in RESTful API development and AI model integration.
- Data Engineer: To optimize data flow between the backend and database.
COST PER ROLE (CALCULATED BASED ON PERSON-MONTH)
- Backend Developer: €5,000/month
- Project Manager: €6,000/month
TOTAL COST OF WP2
€48,000
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 backend developers for 3 months (6 person-months).
MONTH 2
START
MONTH 4
END
TITLE
BACKEND DEVELOPMENT
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 36
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 37
3
WP
MOTIVATION
The car controller is responsible for running the FER model onboard the vehicle. It must collect sensor data, process facial expressions in real-time, and communicate results to the backend. Its design must ensure efficiency, reliability, and low power consumption, as it is a critical system component.
GOALS
1. Implement car controller software to run the FER model in real-time.
2. Establish secure communication between the controller and the backend.
3. Collect sensor data (e.g., speed, braking) and send it to the backend.
4. Optimize performance for vehicle-specific hardware.
MONTH 3
START
MONTH 5
END
TITLE
CAR CONTROLLER DEVELOPMENT
CLASSIFICATION
RESEARCH and
INNOVATION
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 embedded developers for 3 months (6 person-months).
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 38
3
WP
TASKS
1. Hardware Setup:
- Configure the hardware environment (e.g., edge device, GPU, or TPU).
- Install libraries required to run the FER model.
2. FER Model Deployment:
- Adapt the FER model for embedded hardware.
- Test model performance in simulated scenarios.
3. Sensor Data Collection:
- Develop drivers or scripts to read data from the vehicle (e.g., CAN bus).
- Validate collected data and convert it into usable formats.
4. Backend Communication:
- Configure secure communication via RESTful APIs or WebSocket.
- Implement a protocol to transmit FER results and sensor data to the backend.
5. Optimization and Testing:
- Optimize performance to ensure low latency (<500 ms).
- Test in real environments and simulate workloads.
TITLE
CAR CONTROLLER DEVELOPMENT
MONTH 3
START
MONTH 5
END
CLASSIFICATION
RESEARCH and
INNOVATION
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 embedded developers for 3 months (6 person-months).
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 39
3
WP
DELIVERABLES
1. Car Controller Software: Complete code to run the FER model, collect data, and communicate with the backend.
2. Technical Report: Implementation details, hardware configuration, and applied optimizations.
3. Test Logs: Results from tests conducted in simulations and real scenarios.
MILESTONES
1. Completed hardware setup (end of Month 3).
2. FER model deployment finalized (mid-Month 4).
3. Backend communication functioning (end of Month 4).
4. Validation in real environments (end of Month 5).
DEPENDENCIES AMONG WPS
- WP2 (Backend): APIs must be completed to enable communication with the car controller.
- WP5 (Integration): The car controller must be developed and operational for system integration.
TITLE
CAR CONTROLLER DEVELOPMENT
MONTH 3
START
MONTH 5
END
CLASSIFICATION
RESEARCH and
INNOVATION
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 embedded developers for 3 months (6 person-months).
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 40
3
WP
REQUIRED TOOLS OR SOFTWARE
- AI Framework: TensorFlow Lite or PyTorch for running the FER model (available).
- Communication Libraries: Requests or aiohttp for RESTful API.
- Car Controller Hardware: Edge device with GPU support (e.g., NVIDIA Jetson Nano, Coral TPU).
- Simulation Tools: CAN simulators for testing sensor data collection.
REQUIRED ROLES
- Embedded Developer: Specialist in edge devices with expertise in AI and hardware optimization.
COST PER ROLE (CALCULATED BASED ON PERSON-MONTH)
- Project Manager: €6,000/month
- Embedded Developer: €5,500/month
TOTAL COST OF WP2
€51,000
TITLE
CAR CONTROLLER DEVELOPMENT
MONTH 3
START
MONTH 5
END
CLASSIFICATION
RESEARCH and
INNOVATION
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 embedded developers for 3 months (6 person-months).
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 41
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 42
4
WP
MOTIVATION
The mobile app is the main touchpoint between users (passengers and drivers) and the system. It must provide an intuitive and user-friendly interface to view evaluations, complete questionnaires, manage personal data, and interact with the backend. Effective design is essential for an excellent user experience.
GOALS
1. Create an intuitive user interface for passengers and drivers.
2. Implement features for viewing and modifying evaluations and questionnaires.
3. Ensure a smooth user experience and compatibility with Android and iOS devices.
MONTH 5
START
MONTH 6
END
TITLE
FRONTEND DEVELOPMENT (MOBILE APP)
CLASSIFICATION
RESEARCH and
INNOVATION
1 project manager for 2 months (2 person-months).
PERSON-MONTHS
2 frontend developers for 2 months (4 person-months).
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 43
4
WP
TASKS
1. UI/UX Design:
- Create wireframes and mockups for key app sections (e.g., evaluation screens, user profiles).
- Validate design with a sample of users.
2. Implementation of Core Features:
- Integrate with the backend via RESTful APIs.
- Develop screens for viewing and modifying questionnaires generated by FER.
- Create sections for providing manual evaluations (passengers) and viewing evaluations (drivers).
3. Personal Data Management:
- Design a screen for user profile management, allowing data updates and visualization.
- Implement GDPR-compliant policies (e.g., data deletion requests).
4. App Testing:
- Test the app on Android and iOS devices to ensure compatibility and performance.
- Identify and fix bugs.
5. Final Optimization:
- Improve performance (e.g., loading times).
- Apply feedback from user tests.
CLASSIFICATION
RESEARCH and
INNOVATION
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 backend developers for 3 months (6 person-months).
MONTH 2
START
MONTH 4
END
TITLE
FRONTEND DEVELOPMENT (MOBILE APP)
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 44
4
WP
DELIVERABLES
1. Functional Mobile App: Fully operational for Android and iOS devices.
2. Technical Documentation: Details on implementation, APIs used, and deployment instructions.
3. Test Report: Results from tests on real devices.
CLASSIFICATION
RESEARCH and
INNOVATION
MILESTONES
1. Delivery of finalized wireframes and mockups (end of Month 4).
2. Core features implemented (end of Month 5).
3. Complete testing and delivery of the final app version (end of Month 6).
DEPENDENCIES AMONG WPS
- WP2 (Backend): Required to implement and test backend communication.
- WP5 (Integration): Frontend must be completed and tested for system integration.
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 backend developers for 3 months (6 person-months).
MONTH 2
START
MONTH 4
END
TITLE
FRONTEND DEVELOPMENT (MOBILE APP)
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 45
4
WP
CLASSIFICATION
RESEARCH and
INNOVATION
REQUIRED TOOLS OR SOFTWARE
- Development Framework: Flutter or React Native (available).
- Design Tools: Figma or Adobe XD for UI/UX design.
- Communication Libraries: Axios or HTTP for API integration.
- Testing Tools: BrowserStack or real devices for cross-platform testing.
REQUIRED ROLES
- Frontend Developer: Specialist in mobile development, proficient in Flutter/React Native.
COST PER ROLE (CALCULATED BASED ON PERSON-MONTH)
- Project Manager: €6,000/month
- Frontend Developer: €4,000/month
TOTAL COST OF WP2
€20,000
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 backend developers for 3 months (6 person-months).
MONTH 2
START
MONTH 4
END
TITLE
FRONTEND DEVELOPMENT (MOBILE APP)
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 46
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 47
5
WP
MOTIVATION
System integration ensures all components (DB, backend, car controller, and mobile app) communicate effectively. This WP focuses on making the system function cohesively and ensuring data flows seamlessly across components.
GOALS
1. Ensure smooth communication between system components.
2. Validate data flow in real and simulated scenarios.
3. Identify and resolve interoperability issues.
MONTH 7
START
MONTH 8
END
TITLE
SYSTEM INTEGRATION
CLASSIFICATION
SUPPORT and
SERVICES
1 project manager for 2 months (2 person-months).
PERSON-MONTHS
1 system integrator for 2 months (2 person-months).
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 48
5
WP
TASKS
1. Preparation for Integration:
- Review interfaces and APIs exposed by the backend and mobile app.
- Configure a test environment for integration.
2. Backend-Database Integration:
- Validate query handling and data storage.
- Test primary operations (e.g., read/write evaluation data).
3. Backend-Car Controller Integration:
- Validate secure transmission of FER and sensor data from the car controller to the backend.
- Test communication latency.
4. Backend-Frontend Integration:
- Verify functionality of RESTful APIs for the frontend.
- Test core features (e.g., retrieving questionnaires, submitting evaluations).
5. Bug Fixing and Optimization:
- Resolve bugs identified during tests.
- Optimize data flow to reduce latency and improve performance.
TITLE
SYSTEM INTEGRATION
MONTH 7
START
MONTH 8
END
CLASSIFICATION
SUPPORT and
SERVICES
1 project manager for 2 months (2 person-months).
PERSON-MONTHS
1 system integrator for 2 months (2 person-months).
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 49
5
WP
DELIVERABLES
1. Integrated System: All components functioning cohesively.
2. Technical Report: Details on integration, tests performed, and resolved issues.
3. End-to-End Test Logs: Results from real-world simulations and tests.
MILESTONES
1. Backend-database integration completed (end of Week 2, Month 7).
2. Backend-car controller integration completed (end of Month 7).
3. Backend-frontend integration completed (mid-Month 8).
4. End-to-end testing completed (end of Month 8).
DEPENDENCIES AMONG WPS
- WP1 (Database): Database must be complete and functional for backend integration.
- WP2 (Backend): Backend must be operational to integrate with other components.
- WP3 (Car Controller): Car controller must be ready to transmit data to the backend.
- WP4 (Frontend): Mobile app must be completed to test frontend-backend communication.
TITLE
SYSTEM INTEGRATION
MONTH 7
START
MONTH 8
END
CLASSIFICATION
SUPPORT and
SERVICES
1 project manager for 2 months (2 person-months).
PERSON-MONTHS
1 system integrator for 2 months (2 person-months).
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 50
5
WP
REQUIRED TOOLS OR SOFTWARE
- Monitoring Tools: Postman for API testing, Grafana for monitoring data flow.
- Integration Environment: Local or cloud server with dedicated configuration.
- Simulators and Real Tests: CAN simulators for car controller data and real mobile devices for frontend tests.
REQUIRED ROLES
- System Integrator: Specialist in complex system integration, with backend, API, and infrastructure expertise.
COST PER ROLE (CALCULATED BASED ON PERSON-MONTH)
- System Integrator: €6,000/month
- Project Manager: €6,000/month
TOTAL COST OF WP2
€24,000
TITLE
SYSTEM INTEGRATION
MONTH 7
START
MONTH 8
END
CLASSIFICATION
SUPPORT and
SERVICES
1 project manager for 2 months (2 person-months).
PERSON-MONTHS
1 system integrator for 2 months (2 person-months).
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 51
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 52
6
WP
MOTIVATION
The backend is the core of the system, managing data flow between various components: database, car controller, and frontend. It must integrate the FER model, expose RESTful API endpoints, and ensure efficient management of evaluations and collected data, with a strong focus on security and scalability.
GOALS
1. Implement a robust and scalable backend in Python to manage data flow.
2. Integrate the FER model for automatic evaluations.
3. Expose RESTful API endpoints to communicate with the frontend and car controller.
MONTH 2
START
MONTH 4
END
TITLE
SECURITY AND PRIVACY
CLASSIFICATION
RESEARCH and
INNOVATION
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 backend developers for 3 months (6 person-months).
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 53
6
WP
TASKS
1. Development Environment Setup:
- Configure the backend framework (e.g., Flask or FastAPI).
- Structure the project.
2. RESTful API Implementation:
- Create endpoints for communication with the car controller, frontend, and database (e.g., `/sendEvaluation`, `/getUserData`).
- Validate and authenticate API requests.
3. Database Integration:
- Connect to the database using an ORM (e.g., SQLAlchemy).
- Develop backend queries to handle complex data operations (e.g., calculate the average of the last 500 evaluations).
4. FER Model Integration:
- Implement functions to receive input from the car controller.
- Process and store FER data in the database.
5. Security and Privacy:
- Implement security protocols (e.g., TLS 1.3 for communications).
- Encrypt sensitive data.
- Create data management policies compliant with GDPR.
6. Testing and Validation:
- Test APIs (unit tests and integration tests).
- Simulate workloads to ensure scalability.
CLASSIFICATION
RESEARCH and
INNOVATION
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 backend developers for 3 months (6 person-months).
MONTH 2
START
MONTH 4
END
TITLE
SECURITY AND PRIVACY
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 54
6
WP
DELIVERABLES
1. Operational Backend: Complete source code with API and FER model integration.
2. Technical Documentation: Details on implementation, API endpoints, and usage instructions.
3. Data Management Logic: Functions implemented to interact with the database and car controller.
4. Test Report: Results of integration tests and load simulations.
CLASSIFICATION
RESEARCH and
INNOVATION
MILESTONES
1. Delivery of basic working APIs (end of Month 2).
2. Completed database integration (end of Month 3).
3. Backend validation in a simulated environment (end of Month 4).
DEPENDENCIES AMONG WPS
- WP1 (Database): Database design must be completed to develop the backend.
- WP5 (Integration): The backend must be completed to integrate components.
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 backend developers for 3 months (6 person-months).
MONTH 2
START
MONTH 4
END
TITLE
SECURITY AND PRIVACY
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 55
6
WP
CLASSIFICATION
RESEARCH and
INNOVATION
REQUIRED TOOLS OR SOFTWARE
- Backend Framework: Flask or FastAPI (available).
- Security Libraries: PyJWT for authentication, OpenSSL for encryption.
- ORM: SQLAlchemy or equivalent for database interaction.
- Testing Tools: Postman for API testing, pytest for automated tests.
REQUIRED ROLES
- Backend Developer: Specialist in Python, experienced in RESTful API development and AI model integration.
- Data Engineer: To optimize data flow between the backend and database.
COST PER ROLE (CALCULATED BASED ON PERSON-MONTH)
- Backend Developer: €5,000/month
- Project Manager: €6,000/month
TOTAL COST OF WP2
€48,000
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 backend developers for 3 months (6 person-months).
MONTH 2
START
MONTH 4
END
TITLE
SECURITY AND PRIVACY
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 56
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 57
7
WP
MOTIVATION
The backend is the core of the system, managing data flow between various components: database, car controller, and frontend. It must integrate the FER model, expose RESTful API endpoints, and ensure efficient management of evaluations and collected data, with a strong focus on security and scalability.
GOALS
1. Implement a robust and scalable backend in Python to manage data flow.
2. Integrate the FER model for automatic evaluations.
3. Expose RESTful API endpoints to communicate with the frontend and car controller.
MONTH 2
START
MONTH 4
END
TITLE
BACKEND DEVELOPMENT
CLASSIFICATION
RESEARCH and
INNOVATION
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 backend developers for 3 months (6 person-months).
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 58
7
WP
TASKS
1. Development Environment Setup:
- Configure the backend framework (e.g., Flask or FastAPI).
- Structure the project.
2. RESTful API Implementation:
- Create endpoints for communication with the car controller, frontend, and database (e.g., `/sendEvaluation`, `/getUserData`).
- Validate and authenticate API requests.
3. Database Integration:
- Connect to the database using an ORM (e.g., SQLAlchemy).
- Develop backend queries to handle complex data operations (e.g., calculate the average of the last 500 evaluations).
4. FER Model Integration:
- Implement functions to receive input from the car controller.
- Process and store FER data in the database.
5. Security and Privacy:
- Implement security protocols (e.g., TLS 1.3 for communications).
- Encrypt sensitive data.
- Create data management policies compliant with GDPR.
6. Testing and Validation:
- Test APIs (unit tests and integration tests).
- Simulate workloads to ensure scalability.
CLASSIFICATION
RESEARCH and
INNOVATION
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 backend developers for 3 months (6 person-months).
MONTH 2
START
MONTH 4
END
TITLE
BACKEND DEVELOPMENT
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 59
7
WP
DELIVERABLES
1. Operational Backend: Complete source code with API and FER model integration.
2. Technical Documentation: Details on implementation, API endpoints, and usage instructions.
3. Data Management Logic: Functions implemented to interact with the database and car controller.
4. Test Report: Results of integration tests and load simulations.
CLASSIFICATION
RESEARCH and
INNOVATION
MILESTONES
1. Delivery of basic working APIs (end of Month 2).
2. Completed database integration (end of Month 3).
3. Backend validation in a simulated environment (end of Month 4).
DEPENDENCIES AMONG WPS
- WP1 (Database): Database design must be completed to develop the backend.
- WP5 (Integration): The backend must be completed to integrate components.
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 backend developers for 3 months (6 person-months).
MONTH 2
START
MONTH 4
END
TITLE
BACKEND DEVELOPMENT
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 60
7
WP
CLASSIFICATION
RESEARCH and
INNOVATION
REQUIRED TOOLS OR SOFTWARE
- Backend Framework: Flask or FastAPI (available).
- Security Libraries: PyJWT for authentication, OpenSSL for encryption.
- ORM: SQLAlchemy or equivalent for database interaction.
- Testing Tools: Postman for API testing, pytest for automated tests.
REQUIRED ROLES
- Backend Developer: Specialist in Python, experienced in RESTful API development and AI model integration.
- Data Engineer: To optimize data flow between the backend and database.
COST PER ROLE (CALCULATED BASED ON PERSON-MONTH)
- Backend Developer: €5,000/month
- Project Manager: €6,000/month
TOTAL COST OF WP2
€48,000
1 project manager for 3 months (3 person-months).
PERSON-MONTHS
2 backend developers for 3 months (6 person-months).
MONTH 2
START
MONTH 4
END
TITLE
BACKEND DEVELOPMENT
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 61
GANTT CHART
 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9
WP1 |  |  |  |  |  |  |  |  | 
WP2 |  |  |  |  |  |  |  |  | 
WP3 |  |  |  |  |  |  |  |  | 
WP4 |  |  |  |  |  |  |  |  | 
WP5 |  |  |  |  |  |  |  |  | 
WP6 |  |  |  |  |  |  |  |  | 
WP7 |  |  |  |  |  |  |  |  | 
MA non è che qui devo mettere le varie attività?
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 62
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 63
POSSIBLE RISKS
WAIT, WAIT!
WHAT ARE THE POSSIBLE RISKS?
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 64
WAIT, WAIT!
WHAT ARE THE POSSIBLE RISKS?
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 65
RISK
STRATEGY
COST
DEVELOPMENT DELAYS IN WORK PACKAGES (WPS)
INTERNAL RISKS
Problemi di coordinamento tra i team o complessità tecnica sottovalutata.
Implementare una gestione Agile con revisioni settimanali per monitorare i progressi.
Aggiungere risorse temporanee per accelerare i WPs critici.
Formazione e gestione Agile: 3.000€.
Assunzione di risorse aggiuntive: 10.000€.
#1
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 66
RISK
STRATEGY
COST
DEVELOPMENT DELAYS IN WORK PACKAGES (WPS)
INTERNAL RISKS
Problemi di coordinamento tra i team o complessità tecnica sottovalutata.
Implementare una gestione Agile con revisioni settimanali per monitorare i progressi.
Aggiungere risorse temporanee per accelerare i WPs critici.
Formazione e gestione Agile: 3.000€.
Assunzione di risorse aggiuntive: 10.000€.
#2
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 67
RISK
STRATEGY
COST
DEVELOPMENT DELAYS IN WORK PACKAGES (WPS)
INTERNAL RISKS
Problemi di coordinamento tra i team o complessità tecnica sottovalutata.
Implementare una gestione Agile con revisioni settimanali per monitorare i progressi.
Aggiungere risorse temporanee per accelerare i WPs critici.
Formazione e gestione Agile: 3.000€.
Assunzione di risorse aggiuntive: 10.000€.
#3
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 68
RISK
STRATEGY
COST
DEVELOPMENT DELAYS IN WORK PACKAGES (WPS)
EXTERNAL RISKS
Problemi di coordinamento tra i team o complessità tecnica sottovalutata.
Implementare una gestione Agile con revisioni settimanali per monitorare i progressi.
Aggiungere risorse temporanee per accelerare i WPs critici.
Formazione e gestione Agile: 3.000€.
Assunzione di risorse aggiuntive: 10.000€.
#1
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 69
RISK
STRATEGY
COST
DEVELOPMENT DELAYS IN WORK PACKAGES (WPS)
EXTERNAL RISKS
Problemi di coordinamento tra i team o complessità tecnica sottovalutata.
Implementare una gestione Agile con revisioni settimanali per monitorare i progressi.
Aggiungere risorse temporanee per accelerare i WPs critici.
Formazione e gestione Agile: 3.000€.
Assunzione di risorse aggiuntive: 10.000€.
#2
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 70
RISK
STRATEGY
COST
DEVELOPMENT DELAYS IN WORK PACKAGES (WPS)
EXTERNAL RISKS
Problemi di coordinamento tra i team o complessità tecnica sottovalutata.
Implementare una gestione Agile con revisioni settimanali per monitorare i progressi.
Aggiungere risorse temporanee per accelerare i WPs critici.
Formazione e gestione Agile: 3.000€.
Assunzione di risorse aggiuntive: 10.000€.
#3
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 71
REFERENCES
[2]
AUDIOVISUAL AFFECT RECOGNITION FOR AUTONOMOUS VEHICLES: APPLICATIONS, CHALLENGES, AND OPPORTUNITIES (2023)
REVIEW AND PERSPECTIVES ON HUMAN EMOTION FOR CONNECTED AUTOMATED VEHICLES (2023)
[3]
[1]
DRIVER EMOTION RECOGNITION FOR INTELLIGENT VEHICLES: A SURVEY (2020)
https://www.media.mit.edu/publications/driver-emotion-recognition-for-intelligent-vehicles-a-survey/
https://ieeexplore.ieee.org/document/10337780
https://link.springer.com/article/10.1007/s42154-023-00270-z
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.

## Slide 72
PLATFORM-MEDIATED REPUTATION SYSTEMS IN THE SHARING ECONOMY (2020)
[4]
UNDERSTANDING RIDE-SHARING SYSTEMS IN URBAN AREAS: LOCATION, USERS, AND BARRIERS (2020)
[6]
A SYSTEMATIC LITERATURE REVIEW OF RIDE-SHARING PLATFORMS, USER FACTORS, AND BARRIERS (2021)
[5]
https://www.academia.edu/77030822/Platform_mediated_reputation_systems_in_the_sharing_economy_and_incentives_to_provide_service_quality_the_case_of_ridesharing_services
https://etrr.springeropen.com/articles/10.1186/s12544-021-00522-1
https://www.academia.edu/76607239/Understanding_Ride_Sharing_Systems_in_Urban_Areas_The_Role_of_Location_Users_and_Barriers
REFERENCES
Notes: Didi Chuxing implementa il monitoraggio telemetrico della guida (algoritmo di machine learning per verificare frenate brusche, accelerazioni brusche e altri parametri che definiscono una guida pericolosa.